Sep 15 2025

MODULE 4 GROUP ASSIGNMENT

PRABESH RAI | Angelina gochenour | Gladis munoz marin |

heidi schieber | sirona ramahi

ITEC 380: Managing IT Projects

Professor: Jose (Joe) Ascensio

COST & COMMUNICATION MANAGEMENT

1. Project Overview and Goals

This document outlines the communication strategy for updating print and projection hardware across the university campus. The goal is to ensure that all stakeholders receive timely, accurate, and relevant information to support effective decision-making and ensure project success. Clear and consistent communication throughout the project lifecycle will keep the team and stakeholders informed, engaged, and aligned.

2. Stakeholder Analysis

The following table identifies key project stakeholders and their general communication needs.

| Stakeholder | Role | Communication Needs |
| --- | --- | --- |
| Chancellor | Executive | High-level progress and oversight updates, budget status, and immediate updates on issues encountered. |
| Project Manager | Leads the project | All project-related information, detailed status updates, and issue tracking. |
| University IT Department | Manage technical integration and installation | Detailed task assignments, technical specifications, and immediate issue resolution. |
| Finance Office | Handle purchasing, budgeting, and ensure compliance with contract terms | Supply order details, hardware specifications, and updates on budget changes. |
| Academic Departments | End users of hardware | Input on teaching needs and how new hardware can best support classroom activities. |

3. Communication Matrix

The communication matrix is the core of the plan, and it defines how, when, and to whom project information will be shared.

| What Communication Item | Who Sender | Who Recipient | When Frequency | How (Method) | Why (Purpose) |
| --- | --- | --- | --- | --- | --- |
| Group Discussion | Project Team | Project Team | As needed Scheduled | Zoom | Align on project goals |
| Follow-up Emails | Any Team Member | Any Team Member | As needed | KU Email ID | Share updates and follow up |
| Project Documentation | Any Team Member | Project Team | As needed | Word & Excel | Create and share project records |
| Change of Scope Request | Any Team Member | Project Manager | As needed | Written Copy | Formal request scope changes |
| Change of Scope Decision | IT Leadership | Project Manager | As needed | Documentation | Communication scope decisions |
| University Informing | Project Team | University Staff | As needed | Proper Documentation | Record equipment changes |
| Collaboration Documents | Any Team Member | Project Team | Continual | SharePoint | Support ongoing collaboration |
| Installation Updates | IT Leadership | University Staff | Continual | Email/ Posters | Inform users of printer replacements |
| Budget Status Update | Finance office | Project Manager | As needed | Email/ Meeting | Track spending and cost control |

4. Communication Channels and Tools

The project will rely on the following communication channels and tools to ensure smooth coordination and efficient information sharing:

- Email: Used for formal daily communications, key updates, and key announcements.

- Zoom: The primary tool for discussions, task assignments, progress review, and issue tracking.

- SharePoint: Used for collaboration, progress tracking, document sharing, cost updates, and centralized project resource management.

- Printed Notices & Posters: Inform faculty, staff, and students about printer availability, training schedules, and system changes.

- University Website: Post updates on project milestones, training resources, and FAQs for the broader campus community.

5. Roles and Responsibilities

| Role | Communication Responsibilities |
| --- | --- |
| Project Manager | Responsible for all formal communications (status reports, meeting minutes), providing updates to stakeholders, and managing overall project communication flow. |
| University IT Department | Responsible for communicating technical progress, challenges, and coordinating with vendors. |
| Team Leads | Responsible for communicating weekly progress reports to Project Manager, communicating effectively with team members to ensure they are on track, and coordinating team meetings. |
| All Team Members | Responsible for reporting progress on their tasks, issues encountered, and feedback to their team Leads. |

6. Feedback and Escalation Process

Team members and stakeholders can provide feedback during weekly meetings, by email, or through SharePoint. Any project-related issues should be directed to the Project Manager via email. If the problem cannot be resolved within 24 hours, it will be brought to the Project Manager. The Project Manager will then determine if it needs to be escalated to the Project Sponsor for a decision. This plan will be reviewed at the end of each project phase to ensure it remains relevant.

Project Budget Breakdown

| Category | Units/Hrs | Cost/Unit/Hr | Subtotals | WBS Level | % of Total |
| --- | --- | --- | --- | --- | --- |
| 1. Project Management |  |  | $92,500 |  | 23.54% |
| Project manager | 600 hrs | $100/hr | $60,000 |  |  |
| Team coordination/admin | 500 hrs | $65/hr | $32,500 |  |  |
| 2. Hardware |  |  | $120,000 |  | 30.53% |
| Printers & MFDs | 40 units | $2,000/unit | $80,000 |  |  |
| Projectors | 20 Units | $2,000/unit | $40,000 |  |  |
| 3. Software & Setup |  |  | $52,000 |  | 13.23% |
| Licensing & drivers | 40 units | $300/unit | $12,000 |  |  |
| Configuration/testing | 400 hrs | $100/hr | $40,000 |  |  |
| 4. Training & Support |  |  | $38,000 |  | 9.67% |
| Trainer cost | 4 trainers | $4,000 | $16,000 |  |  |
| Trainee sessions | 40 staff | $550 | $22,000 |  |  |
| 5. Disposal & Logistics |  |  | $25,000 |  | 6.36% |
| Old equipment removal | 40 units | $300/unit | $12,000 |  |  |
| Vendor coordination | 130 hrs | $100/hr | $13,000 |  |  |
| 6. Contingency Reserves (20%) |  |  | $65,500 |  | 16.67% |
| TOTAL |  |  | $393,000 |  | 100% |

Cost Baseline by week

| Project Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning and Specifications | $15,000 | $10,000 |  |  |  |  |  | $25,000 |
| Vendor and Logistic Coordination |  | $25,000 |  |  |  |  |  | $25,000 |
| Hardware Procurement |  | $60,000 | $60,000 |  |  |  |  | $120,000 |
| Site Prep, Install and Disposal |  |  | $10,000 | $20,000 | $20,000 |  |  | $50,000 |
| Configuration and Testing |  |  |  |  | $15,000 | $25,000 |  | $40,000 |
| Training and Documentation |  |  |  |  |  |  | $38,000 | $38,000 |
| Final Sign-off and Closure |  |  |  |  |  |  | $2,000 | $2,000 |
| Project Management | $10,000 | $12,000 | $15,000 | $15,000 | $15,000 | $12,500 | $13,000 | $92,500 |
| Contingency Reserve | $5,000 | $5,000 | $5,000 | $5,000 | $5,000 | $5,000 | $5,500 | $40,500 |
| Total by Week | $45,000 | $112,000 | $90,000 | $40,000 | $55,000 | $442,500 | $58,500 | $393,000 |

Cost Estimation

The cost estimation process for the University-Wide Print and Projection Upgrade project was conducted using a bottom-up approach, involving a detailed breakdown of all required activities and resources. This method allowed for estimating costs at the task level, which were then aggregated into broader categories to improve accuracy and control.

Estimations were developed by analyzing expected units, labor hours, and applicable rates for each category. The project budget is organized into key cost categories, including Project Management, Hardware Procurement, Software and Setup, Training and Support, Disposal and Logistics, and Contingency Reserves.

Labor costs, such as configuration, testing, installation, and vendor coordination, were calculated by multiplying estimated work hours by corresponding hourly rates. A contingency reserve of 20% has been allocated to address risks such as schedule delays, supply chain uncertainties, and unforeseen operational disruptions.

Cost estimates were distributed across the project budget breakdown and weekly cost baseline, supporting effective financial monitoring and control throughout the project.

Time Log: