## About
September 9 2025
MODULE 3: GROUP ASSIGNMENT
PROJECT TIME MANAGEMENT: GANTT CHART
PRABESH RAI | ANGELINA GOCHENOUR | GLADIS MUNOZ MARIN | HEIDI SCHIEBER | SIRONA RAMAHI
ITEC 380: MANAGING IT PROJECTS
PROFESSOR: JOSE (JOE) ASCENSIO

## Gantt Chart
[7 empty] | CALENDER LEGEND |  |  | SEPTEMBER | [21 empty] | OCTOBER | [30 empty] | NOVEMBER
| Project Sart Date: | Sep-9-2025
| Project Name: | University-Wide Print and Projection Upgrade |  |  |  |  | PROGESS % | TASK TIMELINE | time axis 2025-09-09 to 2025-11-07
# | Milestone description | Category | Assigned to | Progess % | Progress | Start Date | End Date | Days | Risk
1 | Planning
1.1 | Hardware Specifications | Task | Team | 100% | Complete | 2025-09-09 | 2025-09-12 | 4 | Medium
1.2 | Installation Plan | Task | Team | 50% | In progress | 2025-09-13 | 2025-09-15 | 3 | Low
1.3 | Project Kickoff Meeting | Task | Team | 0% | Not started | 2025-09-16 | 2025-09-19 | 4 | Low
2 | Construct
2.1 | Vendor & Logistic Management | Task | Team | 100% | Complete | 2025-09-20 | 2025-09-21 | 2 | High
2.2 | Equipment Staging & Preparation | Task | Team | 20% | In progress | 2025-09-25 | 2025-09-26 | 2 | Medium
2.3 | Site Preparation-Install & Dispose | Task | Team | 0% | Not started | 2025-09-27 | 2025-09-28 | 2 | Medium
3 | Execution
3.1 | Device Replacement | Task | Team | 0% | Not started | 2025-09-29 | 2025-10-15 | 17 | High
3.2 | Configuration and Testing | Task | Team | 0% | Not started | 2025-10-16 | 2025-10-24 | 9 | Medium
3.3 | Hardware Documentation Package | Task | Team | 0% | Not started | 2025-10-25 | 2025-10-26 | 2 | Low
4 | Closure
4.1 | Scope Validation & Deliverable verification | Task | Team | 0% | Not started | 2025-10-26 | 2025-10-28 | 3 | Medium
4.2 | Completion sign-off Package | Task | Team | 0% | Not started | 2025-10-29 | 2025-10-30 | 2 | Low
4.3 | Final Reflection Report | Task | Team | 0% | Not started | 2025-10-31 | 2025-11-01 | 2 | Low
|  | STATUS | Risk | Category | Team
|  | Not started | Low | Goal | Prabesh Rai
|  | In progress | High | Task | Sirona Ramahi
|  | Blocked | Medium | Milestone | Heidi Schieber
|  | Complete |  |  | Angelina Gochenour
Gladis Munoz Marin
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Type or double click to open date picker.
Note on J6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Days will auto populate, No manual entry needed
Team those dates and % are just random I had to use them to work on the calender section you guys can change them according to your needs. @Prabesh Rai @12:31AM 9/5
I adjusted the closure phases dates to better fit within our 60 day project
I adjusted
I adjusted the dates in the closure part based on our 60-day project. The schedule now assumes we will complete the project one week early, finishing on November 1st instead of the full 60 day limit. or when do you guys want the deadline date to be? - Gladis Munoz - 9/5 (2:08 PMs)
I filled in more of the Task columns and Assigned To columns. Everything else was already filled out. Let me know if there's anything else I should do though! ). I also changed Hardware Specifications
to Medium Risk because the whole point of the project was to redo the hardware because of a new government contract, so it's pretty important for it to meet the specifications, but we can also
change it back to Low Risk. - Heidi Schieber - 9/25 (8:05pm)
For the Planning phase, Hardware specifications were marked complete because they are the foundation for the rest of the project, but as Heidi mentioned , I kept a Medium risk since errors here could impact later work. The installation plan is currently in progress with a Low risk because it depends on finalized specifications. The project kickoff meeting is not started yet but carries only a Low risk since the main concern would be scheduling availability. Please let me know if you guys think otherwise. -Sirona Ramahi- 9/7- 4:13pm